## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) |  |  |  | in hours |  |  |  | Crystal | Sabar | Sam | Samuel | Total
|  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary & | Research React and usage |  | ALL | 10 |  | 5 | 3 | 5 | 5 | 5 | 5
Parallel Tasks | Determine CSS Framework Needed |  | ALL | 2 | 1 | 5 | 1 | 1 | 1 | 1 | 1
| Determine Database |  | ALL | 1 | 5 | 1 | 3 | 1 | 1 | 1 | 1 | 4
| Learn Languages and Frameworks |  | ALL | 5 | 0 | 5 | 3 | 5 | 5 | 5 | 5 | 20
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
0
0
0
0
0
0
Design & Build | Design SiteMaps |  | Samuel | 3 |  | 3 |  |  |  |  | 3 | 3
Iteration 1: | Set up React app on idividual machines |  | ALL | 2 | 5 |  | 0 | 1 | 1 | 1 | 1 | 4
| Set Up Individual Branches in GH |  | ALL | 5 |  |  |  | 1 | 1 | 1 | 1 | 4
| Successfully connect endpoints | [10 empty] | 0
0
0
0
0
0
0
0
[5 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
Iteration 2: | Design Homepage |  | ALL |  | 9 |  | 0 |  |  |  |  | 0
| Design About |  | ALL | 2 | [7 empty] | 0
| Desgin Contact Us |  | Sam | 1 | 1 |  |  |  |  | 1 |  | 1
| Desgin Prices |  | ALL | 2 | [7 empty] | 0
| Design Nav Bar |  | Sam | 2 | 1 |  |  |  |  | 1 |  | 1
| Prices |  | ALL | 2 | [7 empty] | 0
| Design Footer |  | Samuel | 1 | 7 |  | 0 |  |  |  | 10 | 10
| Develop button |  | Samuel | 4 | [6 empty] | 2 | 2
| Merge News pages (RV) |  | ALL | [8 empty] | 0
| Edit Home Page (RV) |  | ALL | [8 empty] | 0
| Edit Info Page (RV) |  | Samuel | 3 | [6 empty] | 4 | 4
0
[5 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
Iteration 3: | Design Homepage |  | Crystal | 6 | 8 | 10 | 0 |  |  |  |  | 0
| Design Cards Components |  | Samuel | [7 empty] | 4 | 4
| Design Carousel component |  | Samuel | 6 | [6 empty] | - | 0
| Design About |  | ALL | [7 empty] | 3 | 3
| Design Contact Us |  | Sam | 2 | [6 empty] | 4 | 4
| Design Prices |  | Samuel |  | 10 |  | 0 |  |  |  |  | 0
| Merge News pages (RV) |  | Sam | 2 | [7 empty] | 0
| Edit Home Page (RV) |  | Samuel | 4 | 4 | [5 empty] | 4 | 4
| Improve SEO (RV) |  | Samuel | 4 | 4 | [5 empty] | 4 | 4
0
0
[5 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
Total |  |  |  | 69 | 55 | 96 | 10 | 14 | 14 | 16 | 52 | 96